## Team
Initials | First | Last | Email | GitHub Username
rp | Ryan | Perretta | rperrett@stevens.edu | ryanperretta6
es | Eleonora | Savova | esavova@stevens.edu | esavova
mb | Matthew | Bayne | mbayne@stevens.edu | mattbayne
sa | Sanjay | Athrey | sathrey@stevens.edu | sathrey24
|  |  | GitHub Repository: | https://github.com/mattbayne/CS-555-Project-Group-7

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | rp | Done
1 | US10 | Marriage after 14 | es | Done
1 | US22 | Unique IDs | rp | Done
1 | US26 | Corresponding Entries | es | Done
1 | US27 | Include individual ages | sa | Done
1 | US29 | List deceased | mb | Done
1 | US30 | List married | mb | Done
1 | US42 | Reject illegitimate dates | rp | Done
1 | US03 | Birth before death | sa | Done
2 | US02 | Birth before marriage | sa | Done
2 | US04 | Marriage before divorce | sa | Done
2 | US07 | Less then 150 years old | mb | Done
2 | US12 | Parents not too old | mb | Done
2 | US40 | Include input line numbers | rp | Done
2 | US05 | Marriage before death | es | Done
2 | US06 | Divorce before death | es | Done
2 | US28 | Order siblings by age | rp | Done
3 | US21 | Correct gender for role | rp | Done
3 | US31 | List living single | rp | Done
3 | US08 | Birth before marriage of parents | sa | Done
3 | US09 | Birth before death of parents | sa | Done
3 | US15 | Fewer than 15 siblings | mb | Done
3 | US16 | Male last names | mb | Done
3 | US18 | Siblings should not marry | es | Done
3 | US23 | Unique name and birth date | es | Done
4 | US25 | Unique first names in families | rp
4 | US33 | List orphans | rp
4 | US34 | List large age differences | mb
4 | US35 | List recent births | sa
4 | US36 | List recent deaths | sa
4 | US38 | List upcoming birthdays | es
4 | US39 | List upcoming anniversaries | es

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2021-03-03 | 32 |  | 0
Sprint 1 | 2021-03-17 | 23 | 9 | 229 | 190 | 1.2053
Sprint 2 | 2021-03-31 | 15 | 8 | 145 | 136 | 1.0662
Sprint 3 | 2021-04-14 | 7 | 8 | 212 | 100 | 2.12
Sprint 4

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US22 | Unique IDs | rp | Done | 5 | 20 | 5 | 5 | Yes
T22.01 | Store ID | rp
T22.02 | Check if ID exists as key in HashMap | rp
US01 | Dates before current date | rp | Done | 25 | 30 | 5 | 15 | Yes
T01.01 | Convert GEDCOM date argument into java.util.Date object | rp
T01.02 | Check if date is before today's date | rp
US42 | Reject illegitimate dates | rp | Done | 25 | 30 | 50 | 20 | Yes
T42.01 | Try to convert GEDCOM date argument into java.util.Date object | rp
T42.02 | Check if conversion fails or not | rp
US29 | List deceased | mb | Done | 15 | 20 | 13 | 20 | Yes
US30 | List living married | mb | Done | 15 | 20 | 13 | 20 | Yes
US03 | Birth before death | sa | Done | 15 | 15 | 15 | 15 | yes
T03.01 | Compare using birth date and potential death date using after() in java.util.Date
US27 | Include individual ages | sa | Done | 30 | 20 | 15 | 20 | yes
T027.01 | Calculate age and account for cases in which individual is already dead | rp
US10 | Marriage After 14 | es | Done | 40 | 45 | 35 | 20 | yes
US26 | Corresponding Entries | es | Done | 75 | 90 | 78 | 55 | yes
Review Results
Keep doing:
Communicating frequently
Giving feedback to other team members
Avoid:
Not committing code to github often
Not pulling from Github enough

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Less then 150 years old | mb | Done | 10 | 10 | 20 | 20 | yes
US12 | Parents not too old | mb | Done | 10 | 10 | 40 | 30 | yes
US02 | Birth before marriage | sa | Done | 10 | 15 | 10 | 1 | yes
T02.01 | Check Family for marriage tag
T02.02 | Check husband/wife if marriage occurs before their birth
US04 | Marriage before divorce | sa | Done | 10 | 15 | 10 | 10 | yes
T04.01 | Check Family for divorce tag
T04.02 | Check Family if marriage occurs before divorce
US40 | Include input line numbers | rp | Done | 5 | 5 | 10 | 5 | yes
T40.01 | Generate Line numbers of errors | rp | Done
T40.02 | Add to the end of error strings | rp | Done
US05 | Marriage before death | es | Done | 10 | 10 | 20 | 20 | yes
T05.01 | Check Family for marriage tag | es | Done
T05.02 | Check if Marriage date exists | es | Done
T05.03 | For both spouces check if death exists | es | Done
T05.04 | For both spouces check if marriage is before death | es | Done
US06 | Divorce before death | es | Done | 10 | 10 | 20 | 20
T06.01 | Check Family for divorce tag | es | Done
T06.02 | Check if divorce date exists | es | Done
T06.03 | For both spouces check if death exists | es | Done
T06.04 | For both spouces check if divorce is before death |  | Done
US28 | Order siblings by age | rp | Done | 20 | 20 | 15 | 30 | yes
T28.01 | Parse file to get all siblings | ALL | Done |  |  |  |  | yes
T28.02 | Get age of all siblings | sa | Done |  |  |  |  | yes
T28.03 | For each family sort siblings | rp | Done |  |  |  |  | yes
Review Results
Keep doing:
Letting each other know when we are pushing to GitHub.
Re-using old helper functions.
Avoid:
Not notifying when we make changes.
Altering other people's code without warning.

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US21 | Correct gender for role | rp | Done | 10 | 15 | 7 | 10 | yes
US31 | List living single | rp | Done | 5 | 5 | 9 | 5 | yes
US08 | Birth before marriage of parents | sa | Done | 10 | 10 | 72 | 10 | yes
US09 | Birth before death of parents | sa | Done | 10 | 10 | 64 | 20 | yes
US15 | Fewer than 15 siblings | mb | Done | 10 | 15 | 17 | 15 | yes
US16 | Male last names | mb | Done | 15 | 15 | 21 | 20 | yes
US18 | Siblings should not marry | es | Done | 15 | 10 | 12 | 10 | yes
US23 | Unique name and birth date | es | Done | 10 | 10 | 10 | 10 | yes
Review Results
Keep doing:
Get work done ahead of time so there is time for integration testing
Avoid:
Lack of communication
Push regularly

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US21 | List recent births | sa |  | 10 | 15
US31 | List recent deaths | sa |  | 10 | 15
US25 | Unique first names in families | rp |  | 5 | 15
US33 | List orphans | rp |  | 6 | 10
US38 | List upcoming birthdays | es |  | 6 | 5
US39 | List upcoming anniversaries | es |  | 10 | 10
US34 | List large age differences | mb |  | 8 | 15

## Stories
Story ID | Story Name | Story Description | Owner
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date | rp
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse | es
US06 | Divorce before death | Divorce can only occur before death of both spouses | es
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people | mb
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce) | sa
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father | sa
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old) | es
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children | mb
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family | mb
US16 | Male last names | All male members of a family should have the same last name | mb
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another | es
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file | es
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent. | es
US27 | Include individual ages | Include person's current age when listing individuals | sa
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file | mb
US30 | List living married | List all living married people in a GEDCOM file | mb
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days | sa
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days | sa
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days | es
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days | es
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors | ALL
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate) | rp